## Sheet1
Timeline
| Previous Timeline | Updated Timeline |  | BEHIND BY: 7 days
2021-05-22 | Invitation Letter from Delta | Invitation Letter from Delta |  | DAYS LEFT: 33 days
2021-05-23 | Conceptualise Design | Conceptualised Design
2021-05-24 |  |  |  | STAGE REACHED: APPROVAL(Pending from Director sir)
2021-05-25 | Worked on Mechanical Design, viewing Delta Products, and figuring out processes | Worked on Mechanical Design, viewing Delta Products, and figuring out processes
2021-05-26
2021-05-27
2021-05-28
2021-05-29
2021-05-30
2021-05-31 | Delta Product List Submission
2021-06-01 | Looking and starting to finalise mechanical parts and processes | Final Delta Product List Submission
2021-06-02
2021-06-03
2021-06-04 |  | Looking and starting to finalise mechanical parts and processes
2021-06-05
2021-06-06 | Asked for approval | Asked for approval, Kazi sir sign Co-ordinated with Sangram sir for manufacturing
2021-06-07 | Signatures from Kazi sir, Daruwala sir and Director sir
2021-06-08
2021-06-09 | Get Approval | Daruwala sir sign
2021-06-10 | Start Manufacturing | base design ready for manufacture special machining parts in the works
2021-06-11 | Explored and start to work on algorithm | Explore and start to work on algorithm
2021-06-12
2021-06-13
2021-06-14
2021-06-15 | Get Delta Products Delivered | Get Approval
2021-06-16
2021-06-17 |  | Start Manufacturing
2021-06-18
2021-06-19 | Complete Algorithm | Complete Algorithm
2021-06-20
2021-06-21
2021-06-22 |  | Get Delta Products Delivered
2021-06-23
2021-06-24
2021-06-25 | Complete Manufacturing
2021-06-26
2021-06-27
2021-06-28
2021-06-29 | Get conveyor
2021-06-30 | Complete PSP Bot-Assembly
2021-07-01 | Work on vision with Conveyor
2021-07-02 |  | Complete Manufacturing
2021-07-03
2021-07-04
2021-07-05
2021-07-06 |  | Get conveyor
2021-07-07 | Complete PSP Bot with Conveyor+ IOT | Work on vision with Conveyor | -7 days to complete
2021-07-08
2021-07-09
2021-07-10
2021-07-11
2021-07-12
2021-07-13
2021-07-14 | Complete Debugging of the model | Complete PSP Bot with Conveyor+ IOT
2021-07-15 | Submission to Delta head | Submission to Delta head
2021-07-16
2021-07-17
2021-07-18
2021-07-19
2021-07-20
2021-07-21
2021-07-22 |  | Complete Debugging of the model
2021-07-23
2021-07-24 | Presentation- DAY 1 | Presentation- DAY 1
2021-07-25 | Presentation- DAY 2 | Presentation- DAY 2